## Slide 1
PETRA III, Status and Upgrade
M. Bieler,
for the PETRA III Team
ESLS XXIV, Lund, 30.11.2016

## Slide 2: Content
PETRA III Overview
PETRA User Operation 2016
Plans for 2017
PETRA IV

## Slide 3: PETRA III Overview
2.3 km circumference
6 GeV electrons
20 damping wigglers
14 (+10) undulator beamlines
1 nm rad x 10 pm rad
100 mA
TopUp operation, 1% beam current variation

## Slide 4: PETRA III Overview
Max von Laue Hall:
1/8 of the circumference of PETRA III
8 double bend acromat cells
14 undulator beamlines:
  2 m Undulators: 11
  5 m Undulators: 3 (2+1)
  5 m Apple Undulator: 1

## Slide 5: User Operation 2016
 | Service Week | 
 | Sunday (User Run) | 
 | Userrun | 
MDT | Machine Development | 
External Users from April 7 to Dec. 22.

## Slide 6: User Operation 2016
Chart: 
| TIMING 40 | TIMING 60 | CONT 240 | CONT 480 | CONT 960
DISTRIBUTION OF OPERATION MODES | 55.1375 | 22.4903 | 0 | 47 | 36.5097
User Run 2016
(as of Nov. 28th)
Scheduled time: 3881 h
48 % Timing Mode (40 or 60 Bunches)
Availability 95.9 %
5 bunch patterns:
Timing Mode
  40 bunches, 192 ns
  60 bunches, 128 ns
Continous Mode
  240 bunches, 32 ns
  480 bunches, 16 ns
  960 bunches, 8 ns
34%
14%
23%
29%
0%

## Slide 7: User Operation 2016
Timing Mode, 40 Bunches:
40 bunches
192 ns
100 mA
2.5 mA per bunch
1.5 h lifetime
Continuous Mode, 960 Bunches:
960 bunches
8 ns
100 mA
100 µA per bunch
15 h lifetime
Problems in Timing Mode:
HOMs in cavities
Radiation damage
Spurious bunches

## Slide 8: User Operation 2016
Timing Mode, 40 Bunches:
HOMs in cavities.
Main source of RF trips 2015: Reflected power.
Main contribution from cavity 2 SL.
March 2016:
Strong vacuum event.
Cavity 2 SL detuned, decoupled from the RF waveguide.
Since then operation with 11 of 12 cavities.
2016:
Plungers at cavity 2 SL exchanged in August, cavity 2 SL back in operation, no more problems.
Reflected power trips mainly occur in timing mode.

## Slide 9: User Operation 2016
Timing Mode, 40 Bunches:
Radiation damage.
Beam life time 1.5 h,
compared to 15 h with 960 bunches.
Radiation levels 10 times higher.
Radiation damage increases.
Single event upsets in electronics:
Spontaneous firing of an injection kicker, only in 40 bunch mode.
2016:
Additional shielding against neutrons introduced, no more problems.
Beam pipe
Kicker magnet
Kicker pulser

## Slide 10: User Operation 2016
Timing Mode, 40 Bunches:
Spurious bunches.
Bunch separation 192 ns.
Typical pump – probe time delays: 150 ns
Spurious bunches at the level of 10-8 disturb the measurements.
The multibunch feedback is used to resonantly excite the spurious bunches > 2 ns and clear them.
Main bunch
Spurious bunches
at -8, 2, 8 ns
Main bunch +/- 2 ns gated out
by the experiments

## Slide 11: Availability 2016
Chart: PETRA III Availability 2016
| 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
AV_W | 0 | 98.4644 | 95.2546 | 97.9398 | 100 | 100 | 90.1273 | 100 | 96.1314 | 89.294 | 89.8148 | 95.1389 | 88.1481 | 100 | 88.2603 | 92.2338 | 95.0926 | 93.9236 | 95.8449 | 100 | 0 | 0 | 97.1655 | 98.1597 | 98.4144 | 100 | 100 | 96.3441 | 99.5377 | 100 | 96.5741 | 98.1713 | 93.7963 | 100 | 95.7691 | 0 | 0 | 0 | 0
TARGET | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95
AV_Y | 0 | 98.4644 | 96.4807 | 97.038 | 97.8567 | 98.3208 | 96.8624 | 96.9782 | 96.8594 | 95.8876 | 95.1963 | 95.1904 | 94.5375 | 94.562 | 94.0532 | 93.9109 | 93.9966 | 93.9917 | 94.1091 | 94.1272 | 94.1272 | 94.1272 | 94.2994 | 94.5165 | 94.724 | 94.9906 | 95.2317 | 95.2431 | 95.4292 | 95.6283 | 95.6678 | 95.7682 | 95.6922 | 95.7002 | 95.7024 | 95.7024 | 95.7024 | 95.7024 | 95.7024
weekly average
goal
yearly average
Studies,
Testruns
95,7 %

## Slide 12: Availability 2016
Chart: 
| RF | PS | WK | IL | VAC | INST | SAFETY | OP | LINAC | UNKNOWN | SEKI | POWER_GLITCH | DESY | FEEDBACK | TIMING | PIA | LONG_INST | INTL | EXP | SCHEDULED
SUM FAULTS | 34 | 17 | 2 | 0 | 4 | 1 | 1 | 3 | 1 | 4 | 2 | 6 | 3 | 3 | 0 | 0 | 0 | 2 | 8 | 0
Chart: 
| RF | PS | WK | IL | VAC | INST | SAFETY | OP | LINAC | UNKNOWN | SEKI | POWER_GLITCH | DESY | FEEDBACK | TIMING | PIA | LONG_INST | INTL | EXP | SCHEDULED
SUM FAILURE TIME | 1.9118 | 1.5028 | 0.52778 | 0 | 0.60972 | 0.069444 | 0.10208 | 0.22917 | 0.056944 | 0.24583 | 0.47361 | 0.43403 | 0.12778 | 0.18472 | 0 | 0 | 0 | 0.18125 | 0.26806 | 0

## Slide 13: Availability 2016
Definition:
Fault: Every beam loss of more than 25%, plus 1 hour (or 1 downtime)
Definition:
Availability =
scheduled beam time
delivered beam time
This rather unique ‘warmup time’
(recommended by MAC in Nov. 2011) reduced the availability in 2016 from 97% to 95.7%

## Slide 14: MTBF 2016
Chart: PETRA III MTBF 2016
| 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
MTBF_W | 0 | 1.8257 | 0.95255 | 1.9588 | 6 | 6 | 0.38626 | 1.2917 | 1.8292 | 1.3394 | 0.67361 | 0.71354 | 0.58765 | 0.29167 | 1.2595 | 1.3835 | 1.4264 | 0.62616 | 1.1501 | 0.29167 | 0 | 0 | 1.3866 | 2.9448 | 2.9524 | 6 | 6 | 0.62222 | 2.841 | 6 | 1.4486 | 1.4726 | 0.80397 | 0.29167 | 1.23 | 0 | 0 | 0 | 0
MTBF_Y | 0 | 1.8257 | 1.3381 | 1.6937 | 2.3603 | 3.027 | 1.4841 | 1.5428 | 1.6429 | 1.6588 | 1.4758 | 1.363 | 1.2484 | 1.2544 | 1.2789 | 1.3098 | 1.3404 | 1.2633 | 1.2733 | 1.2774 | 1.2774 | 1.2774 | 1.3009 | 1.3629 | 1.4235 | 1.5035 | 1.5835 | 1.579 | 1.6323 | 1.7102 | 1.7185 | 1.7274 | 1.6742 | 1.6774 | 1.6762 | 1.6762 | 1.6762 | 1.6762 | 1.6762
Definition:
Mean Time between Failures =
number of faults
delivered beam time
41:00 h

## Slide 15: Status of Extension Beamlines
2 extension beamlines are
operational: PU64, PU65

## Slide 16: Plans for 2017
Shutdowns in Jan/Febr and July/Aug
2017 | Januar | Februar | März | April | Mai | Juni |  | Juli | Aug. | Sep. | Okt. | Nov. | Dez.
1 |  | g j | m p | Test Run | . | . | 1 | . | u w | . |  | MDT | .
2 | a b | g j | m r | Test Run | . | . | 2 | . | u w | . | . | . | .
3 | a b | g j | m r | Test Run | MDT | . | 3 | . | r | . | . | . | .
4 | a b | g | m r | Test Run | . | . | 4 | . | r | . | MDT | . TdoT ? | .
5 | a b |  |  | MDT | . | . | 5 | . | r | . | . | . | .
6 | a b | g j h | A | Test Run | . | . | 6 | s |  | MDT | . | Service | MDT
7 | a b | g j h | A | Test Run | . | MDT | 7 | s | A | . | . | Week | .
8 |  | g j h | A | Test Run | . | . | 8 | s | A | . | . |  | .
9 | c b d f | g j h | A | Test Run | . | . | 9 |  | A | . | . |  | .
10 | c b d f | g j h | A | . | MDT | . | 10 | s t | A | . | . |  | .
11 | c b d f | g j h | A | . | . | . | 11 | s t | A | . | MDT | TdoT ? | .
12 | c b d f |  |  | MDT | . | . | 12 | s t | A | . | . |  | .
13 | c b d f | k | A | . | . | . | 13 | s t |  | MDT | . | . | MDT
14 | c b d f | k | A | . | . | MDT | 14 | s t | Test Run | . | . | . | .
15 |  | k | A | . | Service | . | 15 | s t | Test Run | . | . | MDT | .
16 | c b d f | k | A | . | Week | . | 16 |  | Test Run | . | . | . | .
17 | c b d f | k | A | . | & Ausweich- | . | 17 | s u | . | . | . | . | .
18 | c b d f | k | A | . | termin | . | 18 | s u | . | . | MDT | . | .
19 | c b d f |  |  | . | Interlock | . | 19 | s u | . | . | . | . | .
20 | c b d f | m p | A B | MDT | P22 & 23 | . | 20 | s u | . | MDT | . | . | MDT
21 | c b d f | m p | A B | . |  | MDT | 21 | s u | . | . | . | . | .
22 |  | m p | A B | . | . | . | 22 | s u | . | . | . | MDT | .
23 | e f b a | m p | A B | . | . | . | 23 |  | MDT | . | . | . | Shutdown
24 | e f b a | m p | A B | . | MDT | . | 24 | u w | . | . | . | . | Shutdown
25 | e f b a | m h p | A B | . | . | . | 25 | u w | . | Service | MDT | . | Shutdown
26 | e f b a |  | Test Run | MDT | . | . | 26 | u w | . | Week | . | . | Shutdown
27 | e f b a | m h p | C B | . | . | . | 27 | u w | . |  | . | . | Shutdown
28 | e f b a | m h p | C B | . | . | MDT | 28 | u w | . |  | . | . | Shutdown
29 |  |  | MDT | . | . | . | 29 | u w | . |  | . | MDT | Shutdown
30 | g j |  | C B | . | . | . | 30 |  | MDT |  | . | . | Shutdown
31 | g j |  | C B |  | MDT |  | 31 |  | . |  | . |  | Shutdown

## Slide 17: Plans for Winter 2016/2017
Exchange of one undulator at PU1
Modification of straight section east:
Room for 3 insertion devices for PU21
Installation of front end for PU21 in the tunnel, no hole in the wall
Installation of new undulators PU22-24
Realignment of section east, connection between PXE and old tunnel
Installation of personal interlock for hutches of PU22-24

## Slide 18: Plans for Summer 2017
Exchange of last absorber in damping wiggler section north (PU61)
Installation of front end for PU61 in the tunnel, including a power absorber,
no hole in the wall
Completion of beamline PU21, including the hole in the wall
Installation of personal interlock for hutches of PU21

## Slide 19: PETRA IV, Motivation

## Slide 20: PETRA IV, Parameter Range

## Slide 21: PETRA IV, Timeline

## Slide 22: PETRA IV: Design Strategy
On axis injection with existing injectors
New lattice for the synchrotron
additional booster ring, or linac?
Scaling of the ESRF cell
Phase space exchange solution (double twist in 4D-phase)
Magnet design: quads, combined function magnets and dipoles with longitudinal gradient
girder design: alignment and installation concepts
fast kickers: on axis injection
vacuum design: small chambers
3 arc octants
injection section
undulator sections
x = hor., y = vert.
3 arc octants
y = hor., x = vert.
y <---> x
x <---> y
More details in the following workshop

## Slide 23
Thank you for your attention!