## Slide 1
ESRF Status and upgrade
Jean-Luc Revol
On behalf of the ESRF operation team and the EBS Accelerator Project Team
The XXIV European Synchrotron Light Source Workshop
28-30 November 2016, Elite Hotel Ideon Lund

## Slide 2: acknowledgements
This presentation gathers the works of many ESRF contributors.
A specific acknowledgement must be mentioned to:
JC Biasci, P Raimondi, D Einfeld, K Scheidt, J Chavanne, L Farvacque, S White,
C Benabderrahmane, G LeBec, J Jacob
ISDD engineering group.
I Leconte, L Hardy
who prepared a lot of slides .

## Slide 3: outline
Introduction
Schedule 2015-2020
Operation performance
Project design status
Procurement status
Assembly & Installation Phase

## Slide 4: ESRF EBS: An ambitious new standard for synchrotron storage rings
1024
1023
1022
1021
1020
1019
1018
1017
1016
1015
1014
1013
1012
1011
1010
109
108
107
106
1900 1920 1940 1960 1980 2000 2020
Brilliance (photons/s/mm2/mrad2/0.1%BW)
X-ray tubes
First generation
Second generation
Synchrotron Radiation
Third
generation
ESRF (2014)
ESRF (1994)
ESRF-EBS (2020)
~100 times more brilliant and coherent X-rays
Programme to exploit the qualities of this new and unique extremely brilliant X-ray source:
- Creation of new beamlines
- Innovative detector programme
- « Data as a Service » strategy
ESRF Extremely Brilliant Source
ESRF-EBS – 150 M€ (2015-2022)

## Slide 5: ESRF EBS: An ambitious new standard for synchrotron storage rings
Reduce the horizontal emittance from 4nm to 0.14nm
Beam-line experiments can benefit from : an increase in brilliance
an increase of coherence
(the coherent fraction, in hor. plane)

## Slide 6: brilliance and coherence increase
Undulator: CPMU18,
K=1.68
L=2m
Improved Coherence
Hor. Emittance [nm] | 4 | 0.135
Vert. Emittance [pm] | 4 | 5
Energy spread [%] | 0.1 | 0.09
bx[m]/bz [m] | 37/3 | 6.9/2.6
Coherence
Source performances will
improve by a factor 50 to100
Brilliance
18mm Undulator spectrum

## Slide 7: Extremely Brilliant Source: Accelerator Upgrade
Maintain standard User-Mode Operations until
the day of shut-down for installation
The Extremely Brilliant Source Project aims to:
Substantially decrease the Store Ring Equilibrium Horizontal Emittance
Increase the source brilliance
Increase its coherent fraction
Must fit in the same tunnel : same circumference as much as possible
Keep the electron energy (6 GeV)
IDs at same locations: keep Beamlines where they are
Maintain the existing bending magnets beamlines
Preserve the time structure operation and a multibunch current of 200 mA
Re-use injector complex
Limit the downtime for installation and commissioning to less than 18 months

## Slide 8: Operation and EBS EBS project plan (2015-2020)
01/10/2017 – Start of assembly phase
17/12/2018 – Start of shutdown
– Start of dismantling phase
18/03/2019 – End of dismantling phase
– Start of installation phase
04/11/2019 – End of installation phase
09/01/2020 – Start of beamline commissioning phase
02/12/2019 – Start of storage ring commissioning phase_
January 2017-June 2018 – Delivery of components
May-July 2020 – Friendly Users_
25/08/2020 – Start of USM
1.5 year of User Service Mode interruption
Notes: Mark periods/phases: Design/procurement, Pre-assembly, dismantling, installation

## Slide 9: ESRF today
Storage ring
6GeV, 844 m
Booster synchrotron
200 MeV  6 GeV
300m, 10 Hz
E- Linac
200 MeV
32 straight sections
DBA lattice
42 Beamlines
12 on dipoles
30 on insertion devices
72 insertion devices: 55 in-air undulators, 6 wigglers, 10 in-vacuum undulators, including 3 cryogenic
Accelerator and source division (ASD) mission
Energy | GeV | 6.04
Multibunch Current | mA | 200
Horizontal emittance | nm | 4
Vertical emittance | pm | 4

## Slide 10: Operation : Machine statistics for 2013-2016
 | 2013 | 2014 | 2015 | 2016
Availability (%) | 98.93 | 99.11 | 98.53 | 99.10
Mean Time Between Failures (hrs) | 79.70 | 105.5 | 93.6 | 95.1
Mean duration of a failure (hrs) | 0.86 | 0.94 | 1.37 | 0.86
(Until 22 November 2016)
2014: 52 Failures  1 every 4.4 days
2015: 59 Failures  1 every 3.9 days
USM : 5544 hours (63.3%)
SD : 1944 hours (22.2%)
MDT : 1272 hours (14.5%)
For 2016 (four over five runs ): 42 failures

## Slide 11: Operation 2015: Failure distribution per equipment
 | Number of trip | Total duration (Hours) | Average duration
RF | 30 | 20.0 | 0.7
PSS (Beamlines) | 5 | 5.0 | 1.0
Power Supply | 4 | 3.3 | 0.8
Unexplained | 3 | 1.4 | 0.5
Diagnostics | 3 | 1.2 | 0.4
Human mistake | 3 | 0.8 | 0.3
Master source | 2 | 30.3 | 15.2
INFRA/SRE | 2 | 3.3 | 1.7
Control | 2 | 3.1 | 1.5
Water leak | 1 | 6.4 | 6.4
INFRA/Mains | 1 | 3.5 | 3.5
Front End | 1 | 1.1 | 1.1
INJ / EXT | 1 | 0.3 | 0.3
OPERATION | 1 | 0.2 | 0.2
Grand Total | 59 | 79.9 | 
Preliminary statistics for 2016: 50% of failures due to RF

## Slide 12: Operation 2015: RF failures
Numerous RF trips are due to Arc Detections (14/25) more or less distributed among the RF system, nevertheless a majority on TRA3 (8/14).
Single Cell Cavity: Two trips due to Cavity #1 field breakdown. None from April 2015
SR SSA: Only one trip (bad connection at the On/Off bus)
Noisy signal
Clean signal
+ 30 hours due to the RF master source

## Slide 13: Disaster gallery….
October 2015
Magnet water cooling hoses
Magnet PS circuit breaker short circuit
Radiation damage on cables
Metallic dust in the water circuit

## Slide 14: Operation : Machine
JUNE – JULY 2016 with long periods of deliveries without a failure!

## Slide 15: Operation: filling modes in 2016
16 Bunch in top-up since 26 April 2016
I max = 90 mA,
Refill every 20 mn, delta I = 5 mA, Vertical emittance < 10 pm
skipped refills <2%
8 mA in the single bunch
7/8 + 1
54%

## Slide 16: Operation : Machine
MDT
MDT
MDT
MDT
MDT
MDT
MDT
MDT
UNIFORM 7/8 + 1 16 bunch 7/8 + 1 Hybrid 16 bunch top-up 4*10mA top-up

## Slide 17: Operation: top-up
Injector reliability will increase compared to the past but remains a critical item in top-up
After a long period with minimum intervention, the injection underwent major upgrades in view of the top-up
New Libera Beam Position Monitor electronics
Quadrupole movers
Two additional RF cavities
Linac: New gun, pre-buncher, buncher Third modulator (for redundancy)
A new booster Ramped Injection Power Supply (RIPS) is under commissioning
New power supplies for the septum magnets
Bunch cleaning system
… etc

## Slide 18: Operation: full top-up sequence
The whole injection sequence, including preparation, lasts for 2½ mn
Chart: 
| -200 | 1
 | 0
SYRF on
BPSS on
SY injection on
Linac on
Check Booster
Prepare SR injection
Inject
Check:
Beam in the booster
I < Iref
Otherwise skip injection
Countdown [s]
Warm-up time
Many changes are anticipated with RIPS
Cleaning in the SR

## Slide 19: Operation top-up injection sequence
The present duration of the injection sequence is ~55 s, for a periodicity of 20 mn in 16-bunches
The cleaning in the booster will have 2 benefits:
  the suppression of the perturbations of the stored beam,
  a strong reduction of the top-up duration, down to ~15 s
Validation should occur during this run.
Refill
Cleaning
Chart: 
| -200 | 1
 | 0
Filling up (~12 s, depends on mode and periodicity):
Perturbations due to the kicker bump, at 10 Hz
Will be reduced by a kicker modification (in progress)
Almost inexistent in the future EBS machine
Cleaning in the Storage ring (~40 s):
Vertical emittance blow-up up to 10 pm
Will be suppressed when applying the cleaning in the booster (ready for operation)
t [s]

## Slide 20: Operation top-up: stored beam orbit perturbation
Sources of perturbations to the stored beam:
      The bump is passing through sextupole magnets: amplitude dependent quadrupole field -> bump non-closure and optics functions distortion (beam envelop) In principle the perturbations last a few milliseconds (at 10Hz), but the fast orbit feedback might lengthen the damping)
      The 4 kicker pulse shapes and timing are not strictly identical: bump non closure
      The 4 kickers are slightly misaligned: vertical perturbations
Presently the dominant source of perturbations comes from the sextupole field
The injection in the SR is performed with a 4 kickers orbit bump: in theory no perturbations on the stored beam when it is closed
Significant effort ongoing to implement a passive compensation using copper shims inside the kicker ferrite gap to generate a non linear field in order to cancel the sextupole field.

## Slide 21: Japanese earthquake – perturbation reduction with RF control
22:57:30
the RF-control
is switched-OFF
typical 20 s period
23:04:08
the RF-control
is switched back ON
Sunday 21 November 2016

## Slide 22: New lattice vs present esrf lattice
Present ESRF lattice 32 cells, Double Bend Achromat = (2 dipoles + 15 quad. sext.) per cell ID length = 5 m (standard) / 6m / 7m
ESRF EBS lattice Hybrid 7 Bend Achromat = (4 dipoles + 3 dipoles-quad + 24 quad., sext., oct.) per cell ID length = 5 m
31 magnets per cell instead of 17 currently
Free space between magnets (total for one cell): 3.4m instead of 8m today !!
Dipole
Dipoles-quadrupoles
Dipole
Dipole
Dipole
Dipole
Dipole
5m
6m

## Slide 23: Progress status: Design
Design of all the components nearly completed:
- Magnets ~95% (including Kickers and PM-septa)
- Vacuum System ~95% (One-of-a-kind chambers in injection section in progress)
- Absorbers ~100%
- Girders ~100%
- Supports ~100%
- Diagnostics ~80% (Collimators, Special chambers in progress)
- Power Supplies ~90% (Sizing optimization and hot-swap implementation in progress)
All elements have been fully integrated and are consistent with the overall specifications and requirements

## Slide 24: magnets
132 Dipoles
100 Dipole-quadrupoles
524 Quadrupoles
(132 HG, 392 MG)
196 Sextupoles
98 Correctors
66 Octupoles
More than 1000 Magnets to procure in less than 3 years
Assembled in house
TESLA
TESLA (MG)
DANFYSIK
DANFYSIK (HG)
BINP
SEF

## Slide 25: dipoles
Each dipole based on 5 PM modules
Strength 0.67-0.17 T &
Iron length 1788 mm
25.5 – 30.5 mm GAP
Iron: Pure Iron
Permanent magnet Sm2Co17
Dipole assembly area
PM assembly tool
Around 6000kg of PM, 660 Iron modules,
Partially delivered

## Slide 26: sextupoles
2 types
1700 T/m2 gradient, 166  200 mm length
19.2 mm bore radius
0.5 kW power consumption
Including additional correction coils
Pre-series magnet delivered

## Slide 27: quadrupoles
Moderate Gradient
4 types
Up to 54 T/m gradient, 162 295 mm length
16.4 mm bore radius
0.7  1.1 kW power consumption
High Gradient
2 types
89 & 87 T/m gradient
388  484 mm length
12.7 mm bore radius
1.9 & 1.7 kW power consumption
Pre-series magnet delivered

## Slide 28: Dipole quadrupoles
2 types
Nominal dipole 0.55 – 0.39 T
Nominal gradient 36-39 T/m
1028-800 mm
18.6 mm bore radius
1.6- 1.2 kW power consumption
Poles longitudinally curved
Pre-series magnet in production

## Slide 29: octupoles
36900 T/m3 gradient, 90 mm length
18.6 mm bore radius
0.1 kW power consumption
Allows the required stay clear for Synchrotron radiation fan
Pre-series magnet in production

## Slide 30: correctors
Horizontal: 10 T.mm
Vertical 10 T.mm
Skew quadrupole: 0.12 T
25.5 mm gap mm bore radius
Pre-series magnet delivered

## Slide 31: Girders
5100mm
Four identical girders per cell
Mass of:
Magnetic elements
Supports 6-7T/girder
Vacuum equipements

## Slide 32: girders
Girder supported by 4 adjustable Z feet made of motorised wedges
Y adjustment by 2 manual jacks pushing the girder
X
Z
Y
 | HORIZONTAL (Y) | VERTICAL (Z)
Girder to girder | 50 m | 50 m
Motorized Z adjustment resolution 5m
Manual Y adjustment resolution 5m
1st natural frequency :
- 50Hz (design criteria)
- 49 Hz measured
Z feet optimised for maximum stiffness

## Slide 33: girders
Z movement:
Accuracy: 10.8µm
Repeatability: 3.3µm
Increment: 0.3µm
Preload springs (2x0.7T)
Motorized Wedge Airloc
Vertical movement
Horizontal Jacks functions:
horizontal adjustment
guiding the vertical movement
improoving the stiffness
«Pushing back» spring (3.5T)
Wedge Nivell DK2
Horizontal movement
Pre-series girder delivered by NORTEMECA and AVS
flatness 40mm

## Slide 34: Vacuum chambers
High profile aluminium chambers (dipole magnets + other)
High profile stainless steel chambers (quadrupoles, sextupoles, octupoles)
Low profile stainless steel chambers (inside combined dipole-quadrupoles & HG quadrupoles)
Low profile cross section
20mm
High profile cross section
20mm
High profile cross section
13mm
In situ bake-out
Three main families of chambers:

## Slide 35: Family 1: Aluminium dipole CHAMBERS
4 dipole chambers per cell made of Aluminum
CH2
CH5
CH9
CH13
Design completed
Prototype done
Manufacturing in progress

## Slide 36: Family 2: high profile stainless steel CHAMBERS
CH3
CH12
CH1
Design completed
Manufacturing in progress
High profile cross section
20
Straight Chambers
CH11
CH4
Thick ante-chamber acting as stiffener
1.5 mm sheet EB welding

## Slide 37: Family 3: low profile stainless steel CHAMBERS
Curved chambers
CH6
CH7
CH8
Low profile cross section (inside dipole-quadrupoles and HF quadrupoles)
13
Design complete
Manufacturing in progress

## Slide 38: RF fingers
Patented
8 different bellows = 8 different RF Fingers.
Close collaboration with the vacuum
chamber designer.
FEA model
Prototype tested, additional tests in progress
Design completed
Manufacturing in progress
Blade contact

## Slide 39: Vacuum chambers – CH12 Diagnostics
H stripline
V stripline
Shaker
Current transformer
Beam losses collimator
Procurement in progress
1
2
3
4
4
5

## Slide 40: Photon Absorbers

## Slide 41: photon absorbers
Photon Absorbers
Synchrotron radiation
E Beam
Absorber flange mounted on the ante-chamber
~391 absorbers (including crotch absorbers, without injection cell specials)
Total power to be absorbed: 504.5 kW (30 x 15.795 kW + 2x 15.314) kW
Power density: 10 to 110 W/mm2 (normal to beam)
=> moderate power parameters compared to current ESRF
Scattered radiation blocked in the absorber to avoid chamber cooling
Tight space constraints
CuCr1Zr as an alternative to Glidcop
Integrate the CF flange in the CuCr1Zr absorber body
(Sharma Sushil idea)
All contracts placed, absorbers in production

## Slide 42: Absorbers design : two families
Family Toothed (up to 110 W/mm2)
Family Frontal (up to 50 W/mm2)
ABS CH9-1-29
ABS CH4-1-1
ABS CH5-1-1
ABS CH13-1-13
Crotch 1
No weld, no braze
Temperature photon
Toothed absorber
Toothed geometry optimized to reduce thermal stresses over large area

## Slide 43: Absorbers optimized to block scattered radiation
No water cooling on chambers
Teeth Absorbers intercept the Radiation at grazing angle
Scattered fraction is high (5-10%)
Long End Tooth blocking the Scattered Radiation from reaching the Chamber
Frontal Absorbers intercept Radiation close to Normal Incidence
=> Scattered Fraction is low (<3%)
Screen blocking most of the scattered radiation
Efficiency  85% (Screen + Long Tooth)
60degC local
An average 10W≤ Pscatt ≤30W irradiated on vessels

## Slide 44: 1000 large Power supplies and 1000 small Power Supplies
Type | Name |  | NOMINAL FIELD VALUES |  |  | Electrical design |  |  | PS |  |  |  | nom | maxWatt
 |  | quantity | Length | dB/dx | lattice | Power | Voltage | Current | OVdesign |  | Watts | Watts | Watts | P total
 |  | per cell | [m] | [T/m] |  | [kW] | [V] | [A] | factor | Imax | Pnom | Pmax | cell | cell
Quadrupole, mod. gradient | QF1 | 2 | 0.349 | 53.7 |  | 1.06 | 12.1 | 87.5 | 1.2 | 102 | 1167 | 1576 | 2334 | 3152
Quadrupole, mod. gradient | QD2 | 2 | 0.266 | 51.5 |  | 0.86 | 9.8 | 87.5 | 1.2 | 106 | 966 | 1418 | 1932 | 2836
Quadrupole, mod. gradient | QD3 | 2 | 0.216 | 46.5 |  | 0.74 | 8.4 | 87.5 | 1.2 | 117 | 843 | 1519 | 1687 | 3037
Quadrupole, mod. gradient | QF4 | 4 | 0.216 | 51.5 |  | 0.74 | 8.4 | 87.5 | 1.2 | 106 | 843 | 1238 | 3373 | 4952
Quadrupole, mod. gradient | QD5 | 2 | 0.212 | 52.5 |  | 0.86 | 9.8 | 87.5 | 1.2 | 104 | 966 | 1364 | 1932 | 2729
Total |  | 12 |  |  |  |  |  |  |  |  |  |  | 11257 | 16705
Quadrupole, high gradient | QF6 | 2 | 0.36 | 95.2 |  | 1.42 | 15.7 | 90.4 | 1.1 | 99 | 1535 | 1857 | 3070 | 3714
Quadrupole, high gradient | QF8 | 2 | 0.48 | 96.2 |  | 1.66 | 18.6 | 89 | 1.1 | 98 | 1767 | 2139 | 3535 | 4277
Total |  | 4 |  |  |  |  |  |  |  |  |  |  | 6605 | 7992
Dipole-Quadrupole, high field | DQ1 | 2 | 1.11 | 37.54 | 33.9 | 1.59 | 15.75 | 100.7 | 1.2 | 121 | 1729 | 2490 | 3458 | 4980
Dipole-Quadrupole, mod field | DQ2 | 1 | 0.77 | 37.04 | 33.7 | 1.38 | 17.0 | 81.0 | 1.2 | 97 | 1469 | 2116 | 1469 | 2116
Total |  | 3 |  |  |  |  |  |  |  |  |  |  | 4928 | 7096
Sextupole, long | SD | 4 |  | 4500 | 4300 | 1.01 | 11.7 | 86 | 1.1 | 95 | 1111 | 1344 | 4444 | 5377
Sextupole, long | SF | 2 |  |  |  | 1.01 | 11.7 | 86 | 1.1 | 95 | 1111 | 1344 | 2222 | 2689
Total |  | 6 |  |  |  |  |  |  |  |  |  |  | 6666 | 8066
Octupole | OF1-2 | 2 | 0.1 |  |  | 0.30 | 3.2 | 94 | 1.2 | 113 | 426 | 613 | 852 | 1226
Total |  | 2 |  |  |  |  |  |  |  |  |  |  | 852 | 1226
 |  | 27 | Total PS power for one cell for main electromagnets |  |  |  |  |  |  |  |  |  | 30.3 | 41.1
 |  |  |  |  |  |  |  |  |  |  |  |  | KW | KVA
 |  | magnet | coils |  | type |  |  |  |  |  |  |  |  | 
corrector AC+DC (5 independent coils) |  | 3 | 5 |  | AC+DC |  |  |  |  |  |  |  |  | 
Sextupole, short correctors |  | 6 | 6 |  | DC |  |  |  |  |  |  |  |  | 
Total number of coils/cell |  |  | 51 |  |  |  |  |  |  |  |  |  |  | 
About 1000 DC-DC low voltage converters: the average channel power is around 1kW and a maximum of 2.3kW.
The stability requested will be 15ppm with a MTBF of more than 400 000 hours.
The integration in 32 cabinets will be designed with the Computer Services for redundancy and HOT-Swappability
Contracts in place by December 2016

## Slide 45: RF Layout
Storage Ring
Teststand
KLYS 2
Cell 7
KLYS 1
Cell 5
75 kW
tower
75 kW
tower
75 kW
tower
75 kW
tower
75 kW
tower
75 kW
tower
3x existing 150 kW SSAs
3rd harmonic cavities
  under study
In
house
SSA
Cell 25
-7 dB
-7 dB
5 cell cavities replaced by 14 HOM damped single cavities
Keep the existing transmitters

## Slide 46: RF cavities
Cavity assembly area
Fabrication of 12 HOM damped cavities by RI
4 cavity delivered
2 cavities conditioned o 750 kV within 2 weeks

## Slide 47: Front-ends
ID Front-End
BM Front-End
Front-Ends new design (completed) for :
SR junction chambers
BM FE photon shutter unit
Procurement in progress
42 Front-Ends
28 ID FE’s
14 BM FE’s

## Slide 48: Bending magnets source: 2-pole, 3-Pole or short wigglers
Half assembly
Field Customized
Large fan with flat top field
2 mrad feasible for 1.1 T 3PW
Mechanical length ≤ 150 mm
Source shifts longitudinally by ~3m
Source shifts horizontally by ~1-2cm
Flux from 3PW
All new projects of diffraction limited storage rings have to deal with:
Increased number of bending magnets / cell => BM field reduction
Conflict with hard X-ray demand from BM beamlines
ESRF will go from 0.85 T BM to 0.54 T BM
The BM Sources will be replaced by dedicated 2-Pole or 3-Pole Wigglers

## Slide 49: mockup
Many tests have been made with the prototype mockup:
Girder performances
Girder handling
Survey
Thermal issues
Compatibility checks
Services and cabling optimization
A full cell mockup will be built from January 2017:
4 fully assembled girders will
be used to test and optimize the
assembly and installation sequences

## Slide 50: Buildings for the assembly and installation phase
ESRF 1 Girder assembly hall & ESRF2 Storage buildings
ESRF 10-11-12-13 Temporary building for storage and dismantling
All critical contracts for logistic in place
Chartreuse hall for dipole assembly assembled girder storage

## Slide 51: Girders assembly in ESRF01

## Slide 52: Assembly phase
Assembling of magnets on the girders
Assembling of vacuum chambers on dedicated tables
Then opening of magnets and add the whole vacuum section,… alignment,…..
All the girders will be assembled in ESRF1 (Sep 2017 - Oct 2018)
and stored mainly in the Chartreuse hall before the Long Shutdown

## Slide 53: Dismantling and infrastructure preparation
The tunnel must be cleaned up prior the installation of the new machine.
Some work/upgrade will be anticipated prior the long shutdown
The existing machine will be dismounted using the cranes
Each component of the present storage ring must be fully dismounted, radiation measured, traced and stored following French safety regulation.
Some civil work needed prior rolling the new girders.

## Slide 54: Installation
Normally access for ordinary maintenance is via the roof, using over-head cranes,
but …. Assembled girders are too heavy for the cranes Specific handling tools.

## Slide 55: Dismantling & installation planning
Dismantling and installation sequence has be evaluated and a preliminary schedule prepared

## Slide 56: Conclusion
EBS officially started on January 1st 2015
No impact on user operation
Continuation of the development (injector, top-up, cryo undulators,…)
Project execution progression:
Engineering Design virtually completed
Procurement in full swing
Delivery of all pre-series components expected by end 2016/ start 2017
 Schedule now heavily linked to external manufacturers!
Assembly to be started in less than 1 year (mock spring 2017)
Dismantling/installation/commissioning in preparation
At this stage, no major show stopper identified.

## Slide 57: Many thanks for your attention

## Slide 58: Lifetime of S28B
S28B
DA -10mm@S3
TLT ~ 21h
S28A
DA -8.1mm@S3
TLT ~ 13h.
ey=5pm | ESRF | Upgrade
Multibunch | 64 h | 21 h
16 bunch | 6 h | 2.1 h
4 bunch | 4 h | 1.4 h

## Slide 59: Collimation optimization to decrease losses in the IDs

## Slide 60: Collimator shielding 50 cm LEAD local shielding
mSv/h
0.5
ambient dose equivalent rate (mSv/h)
0.5
cm
total
neutrons